## PM02
Plant | Planned | Executed | Month
C2C3 | 38 | 38 | JUNE
LPG | 39 | 39 | JUNE
HVJ | 37 | 37 | JUNE
C2C3 | 44 | 44 | JULY
LPG | 32 | 32 | JULY
HVJ | 36 | 36 | JULY

## PM01
Plant | Planned | Executed | Month
C2C3 | 89 | 89 | JUNE
LPG | 102 | 102 | JUNE
HVJ | 33 | 33 | JUNE
C2C3 | 92 | 92 | JULY
LPG | 145 | 145 | JULY
HVJ | 43 | 43 | JULY

## Breakdown Maintenance
Plant | No. of Breakdown Jobs | Short description of the job | Month
C2C3 | 0 |  | JUNE
LPG | 0 |  | JUNE
HVJ | 0 |  | JUNE
C2C3 | 2 | Casing leak in 16-PA-107 B, LP Compressor-B Third stage high vibration failure | JULY
LPG | 1 | Thermax VAM tripped due to PT malfunctioning | JULY
HVJ | 2 | DVPL EOT WHEEL REPLACEMENT, HRSG-C, Sample line de-chocked work | JULY

## Jobs Hold for Shutdown
Plant | No. of Jobs hold | Short description of the job | Month
C2C3 | 0 |  | JUNE
LPG | 1 | LGC-1 GT Bearing No. 4 Oil Leakage to be attended | JUNE
HVJ | 0 |  | JUNE
C2C3 | 0 |  | JULY
LPG | 0 |  | JULY
HVJ | 0 |  | JULY

## Vibration Monitoring
Plant | No. of Equipment Scheduled | No. of Equipment Monitored (Executed) | Reasons for Equipment not monitored | No. of Equipment With Normal Health | Health Index | No. of Equipment With Critical Health | Critical Index | Corrective Actions Initiated | Corrective Actions Pending | Short Description of Issue and Action taken/Reasons for actions pending | Month
C2C3 | 199 | 195 | 1 M/c under standby | 194 | 0.99487 | 1 | 0.0051282 | 1 | 0 | DEGASSED AIR BLOWER-A Alignment corrected | JUNE
LPG | 235 | 229 | 2 M/c under shutdown as per operational requirement | 228 | 0.99563 | 1 | 0.0043668 | 1 | 0 |  | JUNE
HVJ | 71 | 67 | 1.K01E GAS TURBINE STANDBY, K01E COMPRESSOR STANDBY, DVPL IA COMP RADIATOR FAN-2 MAINTENANCE, VDPL GTC-A LOC-2 MOTOR MAINTENANCE | 65 | 0.97015 | 2 | 0.029851 | 2 | 0 | DVPL GTC-C FAN 2 & DVPL GTC-C FAN 6 - Belt tension adjusted and alignment corrected. | JUNE
C2C3 | 199 | 196 | LP compressor-B Breakdown, LEAN AMINE CHARGE PUMP-D in stopped conditon, DIESEL ENGINE -A (FWPH) under maintenance. | 196 | 1 | 0 | 0 | 0 | 0 |  | JULY
LPG | 287 | 274 | MACHINE UNDER SHUT DOWN - 08 No. 1) PRU-1 GT, 2) PRU-1 COMPR, 3) PRU-2 GT, 4) PRU-2 COMPR, 5) DED F . W. PUMP - B, 6) RAIL LDNG PUMP - B, 7) NAPTHA PUMP-B (PH-2), 8) NAPTHA PUMP-A (PH-2) MACHINE UNDER MAINTENANCE - 05 No 1) STP-2 SDM PUMP- C, 2) STP-2 SUBMERSIBAL PUMP-2, 3) STP-1 RECIRCULATION PUMP- 2, 4) COOLING TOWER FAN-3 AUDITORIUM BLD, 5) COND WATER PUMP-4 AUDITORIUM BLD, | 271 | 0.98905 | 3 | 0.010949 | 1 | 2 | 1) STP-1 SUBMERSIBAL PUMP-1 : MOTOR vibration problem found, concern dept. has been informed. 2) HVAC COMPRESSOR-1 : Internal Bearing inspection to be done, status : Pending. 3) CONDENSATE WATER PUMP-1 : Job completed (Problem: Shaft damage) | JULY
HVJ | 69 | 63 | 1.GTC M/L-A GG STANDBY 2. GTC M/L-A COMP STANDBY 3. VDPL GTC-A GG STANDBY 4.VDPL GTC-A COMP STANDBY 5. VDPL GTC-A LOC-2 MAINTENANCE 6. VDPL IA COMP RADIATOR FAN-1 | 61 | 0.96825 | 2 | 0.031746 | 2 | 0 | LOOSENESS OF BELT AND MISLAIGNMENT IN DVPL GAC-1 & DVPL LOC-1. GREASING, ALIGNMENT AND BELT TIGHTENING ENSURED | JULY